## Project_Tasks
Task_ID | Task_Name | WBS | Responsible | Planned_Start | Planned_Finish | Actual_Start | Actual_Finish | Duration_Planned_Days | Duration_Actual_Days | Planned_Progress_% | Actual_Progress_% | Status
T-01 | Site Mobilization | 1.1 | Civil Team | 45292 | 45306 | 45292 | 45306 | 14 | 14 | 1 | 1 | Completed
T-02 | Excavation & Earthworks | 1.2 | Civil Team | 45302 | 45323 | 45305 | 45329 | 21 | 24 | 1 | 1 | Completed
T-03 | Foundation Piling | 1.3 | Structural Team | 45320 | 45350 | 45325 |  | 30 | 33 | 1 | 0.95 | Delayed
T-04 | Substructure Concrete | 1.4 | Structural Team | 45347 | 45372 | 45354 |  | 25 | 27 | 0.9 | 0.8 | Delayed
T-05 | Superstructure – Level 1 | 2.1 | Structural Team | 45370 | 45390 | 45374 |  | 20 | 16 | 0.7 | 0.6 | Delayed
T-06 | Superstructure – Level 2 | 2.2 | Structural Team | 45387 | 45407 | 45397 |  | 20 | 16 | 0.4 | 0.3 | Delayed
T-07 | MEP Rough-In – Level 1 | 3.1 | MEP Team | 45392 | 45410 | 45398 |  | 18 | 10 | 0.35 | 0.25 | Delayed
T-08 | MEP Rough-In – Level 2 | 3.2 | MEP Team | 45407 | 45425 |  |  | 18 |  | 0.1 | 0 | Not Started
T-09 | Facade & Cladding | 4.1 | Facade Team | 45412 | 45442 |  |  | 30 |  | 0.1 | 0 | Not Started
T-10 | Interior Fit-Out | 4.2 | Interior Team | 45440 | 45465 |  |  | 25 |  | 0.1 | 0 | Not Started
T-11 | Testing & Commissioning | 5.1 | QA Team | 45462 | 45476 |  |  | 14 |  | 0.1 | 0 | Not Started
T-12 | Final Inspection & Handover | 5.2 | PM Team | 45474 | 45481 |  |  | 7 |  | 0.1 | 0 | Not Started

## Cost_Tracker
Task_ID | Task_Name | Cost_Category | Planned_Cost_USD | Actual_Cost_USD | Cost_Variance_USD | Cost_Variance_% | Earned_Value_USD | CPI | SPI
T-01 | Site Mobilization | Preliminaries | 45000 | 44500 | -500 | -0.011111 | 45000 | 1.0112 | 1
T-02 | Excavation & Earthworks | Civil | 120000 | 131000 | 11000 | 0.091667 | 120000 | 0.91603 | 1
T-03 | Foundation Piling | Structural | 280000 | 298000 | 18000 | 0.064286 | 266000 | 0.89262 | 0.95
T-04 | Substructure Concrete | Structural | 175000 | 168000 | -7000 | -0.04 | 140000 | 0.83333 | 0.8
T-05 | Superstructure – Level 1 | Structural | 210000 | 195000 | -15000 | -0.071429 | 126000 | 0.64615 | 0.6
T-06 | Superstructure – Level 2 | Structural | 210000 | 82000 | -128000 | -0.60952 | 63000 | 0.76829 | 0.3
T-07 | MEP Rough-In – Level 1 | MEP | 95000 | 28000 | -67000 | -0.70526 | 23750 | 0.84821 | 0.25
T-08 | MEP Rough-In – Level 2 | MEP | 95000 | 0 | -95000 | -1 | 0 | - | 0
T-09 | Facade & Cladding | Architectural | 185000 | 0 | -185000 | -1 | 0 | - | 0
T-10 | Interior Fit-Out | Architectural | 320000 | 0 | -320000 | -1 | 0 | - | 0
T-11 | Testing & Commissioning | QA | 40000 | 0 | -40000 | -1 | 0 | - | 0
T-12 | Final Inspection | Management | 25000 | 0 | -25000 | -1 | 0 | - | 0
TOTAL |  | All Categories | 1800000 | 946500 | -853500 |  | 783750

## ⚙️ Config
CONFIGURATION – Change column names here if your real file is different
Field | Current Column Name in Excel | Description | Required?
task_id | Task_ID | Unique ID for each task | Yes
task_name | Task_Name | Description of the task | Yes
planned_start | Planned_Start | Planned start date (date format) | Yes
planned_finish | Planned_Finish | Planned finish date (date format) | Yes
actual_start | Actual_Start | Actual start date (blank if not started | Yes
actual_finish | Actual_Finish | Actual finish date (blank if not done) | No
planned_progress | Planned_Progress_% | Planned % complete (0–1 or 0–100) | Yes
actual_progress | Actual_Progress_% | Actual % complete (0–1 or 0–100) | Yes
status | Status | Task status label | No
planned_cost | Planned_Cost_USD | Budget for each task | Yes
actual_cost | Actual_Cost_USD | Spent so far | Yes
earned_value | Earned_Value_USD | EV = Planned Cost × Actual % | Auto
📝 HOW TO USE:
1. If your real Excel file uses different column headers, update column B above.
2. The pipeline script reads column B to find the right columns automatically.
3. Keep the Field names in column A unchanged – they are referenced by the code.